## A&E Projects
Project Type | Session | LRBP Ranking | Project Number | Project Name | Location | Amount | Consultant Appointment | Preliminary Bid Date | Estimated Bid Quarter | Project Status | Project Manager
CAPITAL DEVELOPMENT | 68 | FWP-07 | 2023-38-02 | Seedling Nursery Improvements | Missoula | 2797320 | A/E Appointed | Already Bid |  | On Hold | Nick Franz
MAJOR REPAIR | 68 | MR-50 | 2023-02-29 | Hamilton Hall Life-Safety System Improvements | Bozeman | 2400000 | A/E Appointed | Already Bid |  | Design | Marina Little
CAPITAL DEVELOPMENT | 68 | CD-11 | 2023-12-12 | New Multi-Purpose Programs Building | Deer Lodge | 9000000 | A/E Appointed | Already Bid |  | Design | Marina Little
MAJOR REPAIR | 69 | MR-43 | 2025-12-06 | MSP MCE Restroom Repairs | Deer Lodge | 200000 | A/E Appointed | Already Bid |  |  | Marina Little
MAJOR REPAIR | 68 |  | 2023-31-05 | Clearwater Junction RV Dump Station Repair & Reno | Greenough | 1600000 | A/E Appointed | Already Bid |  | On Hold | Mark Hines
MAJOR REPAIR | 68 | MR-43 | 2023-02-32 | WARC Shop Renovation & Safety Upgrades | Corvallis | 600000 | A/E Appointed | Already Bid |  | On Hold | Nick Franz
CAPITAL DEVELOPMENT | 68 |  | 2023-31-02 | Combination Facility Kalispell | Kalispell | 11000000 | A/E Appointed | Already Bid |  | Bidding | Nick Franz
MAJOR REPAIR | 68 | MR-23 | 2023-01-05 | FLBS Roof Replacements | Yellow Bay | 262000 | A/E Appointed | Already Bid |  | Bidding | Nick Franz
MAJOR REPAIR | 69 | MR-41 | 2025-30-10 | Capitol Building Interior Lighting Restoration | Helena | 125000 | A/E Appointed | Already Bid |  | Bidding | Russ Katherman
CAPITAL DEVELOPMENT | 68 |  | 2023-33-19 | Helena Readiness HVAC | Helena | 3340668 | A/E Appointed | 2026-01-20 | Q1 2026 | Design | Chris Batson
MAJOR REPAIR | 68 |  | 2023-33-19-01 | Helena Readiness Temperature Controls | Helena | 1200000 | A/E Appointed | 2026-01-20 | Q1 2026 | Design | Chris Batson
CAPITAL DEVELOPMENT | 68 |  | 2023-31-01 | Combination Facility Great Falls | Great Falls | 12600000 | A/E Appointed | 2026-01-22 | Q1 2026 | Bidding | Nick Franz
MAJOR REPAIR | 69 | MR-13 | 2022-07-01-01 | Helena College Donaldson/Airport Boiler System | Helena | 150000 | A/E Appointed | 2026-02-28 | Q1 2026 | Design | Mark Hines
MAJOR REPAIR | 69 | MR-09 | 2022-06-01-01 | UM Montana Tech Campus Heating Plant Boiler System | Butte | 2400000 | A/E Appointed | 2026-03-01 | Q1 2026 | Design | Mark Hines
MAJOR REPAIR | 69 | MR-26 | 2023-20-02A | Completion of Parking Lot Improvements | Great Falls | 780000 | A/E Appointed | 2026-03-10 | Q1 2026 | Design | Chris Batson
CAPITAL DEVELOPMENT | 68 | CD-30 | 2023-02-36 | BART Life-Safety & Programmatic Improvements | Bozeman | 10000000 | A/E Appointed | 2026-03-12 | Q1 2026 | Design | Nick Franz
MAJOR REPAIR | 69 | MR-30 | 2025-04-03 | UM-W Steam Distribution System Upgrades | Dillon | 475000 | A/E Appointed | 2026-03-15 | Q1 2026 | Planning | Mark Hines
MAJOR REPAIR | 69 | MR-15 | 2025-04-02 | UM-W Swysgood Tech Center HVAC Cooling System Repl | Dillon | 370000 | A/E Appointed | 2026-03-15 | Q1 2026 | Planning | Mark Hines
MAJOR REPAIR | 68 |  | 2023-19-01 | MMHNCC Key Card Entry System | Lewistown | 125000 | A/E Appointed | 2026-03-15 | Q1 2026 | Design | Nick Franz
MAJOR REPAIR | 69 | MR-02 | 2023-19-01A | MMHNCC Completion of Door Access Controls | Lewistown | 130000 | A/E Appointed | 2026-03-15 | Q1 2026 | Design | Nick Franz
CAPITAL DEVELOPMENT | 68 |  | 2023-35-07 | Beartooth WMA Facilities Upgrade | Wolf Creek | 8000000 | A/E Appointed | 2026-03-15 | Q1 2026 | Design | Nick Franz
MAJOR REPAIR | 69 | MR-05 | 2023-19-01 | MMHNCC Additional Security Cameras | Lewistown | 300000 | A/E Appointed | 2026-03-16 | Q1 2026 | Design | Nick Franz
MAJOR REPAIR | 69 | MR-44 | 2025-37-02 | Air Conditioning Installation | Helena | 300000 | A/E Appointed | 2026-03-19 | Q1 2026 | Design | Mark Hines
AUTHORITY ONLY | 69 |  | 2025-01-11D | Women's Soccer Locker Room Remodel & Lighting | Missoula |  | A/E Appointed | 2026-03-21 | Q1 2026 | DELEGATED
MAJOR REPAIR | 69 | MR-06 | 2025-04-01 | UM-W Selected Fire Alarm Upgrades | Dillon | 500000 | A/E Appointed | 2026-04-01 | Q2 2026 | Planning | Mark Hines
CAPITAL DEVELOPMENT | 69 | CD-80 | 2025-01-10D | South Campus Tennis Court Complex | Missoula | 8300000 | A/E Appointed | 2026-04-01 | Q2 2026 | DELEGATED
MAJOR REPAIR | 68 |  | 2015-01-01-04 | Music Building Elevator Upgrade | Missoula | 37625 | A/E Appointed | 2026-04-01 | Q2 2026 | Design | Russ Katherman
MAJOR REPAIR | 69 | MR-37 | 2025-06-02 | MT Tech Science & Engineering & ELC Building Eleva | Butte | 400000 | A/E Appointed | 2026-04-15 | Q2 2026 | Planning | Mark Hines
MAJOR REPAIR | 69 | MR-45 | 2025-06-03 | MT Tech Mining & Geology Building Temp Controls | Butte | 300000 | A/E Appointed | 2026-04-15 | Q2 2026 | Planning | Mark Hines
MAJOR REPAIR | 69 | MR-21 | 2025-05-02 | Automotive Technology Building Roof Replacement | Havre | 460000 | 2026-01-20 | 2026-04-21 | Q2 2026 | Planning | Chris Batson
MAJOR REPAIR | 69 | MR-17 | 2025-02-07 | MSU Linfield Hall Roof Replacement | Bozeman | 850000 | A/E Appointed | 2026-04-22 | Q2 2026 | Design | Marina Little
CAPITAL DEVELOPMENT | 68 |  | 2023-31-03 | Combination Facility Missoula | Missoula | 10500000 | A/E Appointed | 2026-04-24 | Q2 2026 | On Hold | Nick Franz
MAJOR REPAIR | 68 | MR-27 | 2023-03-02 | Campus Water Distribution System Upgrades | Billings | 1911000 | A/E Appointed | 2026-04-24 | Q2 2026 | Design | Mark Hines
MAJOR REPAIR | 69 | MR-11 | 2025-07-02 | GFC Campus Heating & Domestic Hot Water Upgrades | Great Falls | 400000 | A/E Appointed | 2026-04-28 | Q2 2026 | Design | Chris Batson
MAJOR REPAIR | 69 | MR-10 | 2025-44-01 | State Grain Lab Heating System Upgrades | Great Falls | 150000 | A/E Appointed | 2026-04-28 | Q2 2026 | Design | Chris Batson
CAPITAL DEVELOPMENT | 69 | CD-27 | 2025-33-05 | New Training Drop Zone | MTANG | 1800000 | A/E Appointed | 2026-05-01 | Q2 2026 | Planning | Russ Katherman
MAJOR REPAIR | 69 | MR-19 | 2025-05-01 | MSU-N Cowan Hall Exterior Envelope Upgrades | Havre | 1725000 | A/E Appointed | 2026-05-12 | Q2 2026 | Design | Chris Batson
MAJOR REPAIR | 68 |  | 2023-30-09 | Roof & Mechanical - DPHHS 111 N. Sanders St. | Helena | 1309099 | A/E Appointed | 2026-05-20 | Q2 2026 | Planning | Russ Katherman
MAJOR REPAIR | 68 |  | 2023-30-10 | Roof Replacement - FWP Headquarters | Helena | 289695 | A/E Appointed | 2026-05-20 | Q2 2026 | Planning | Russ Katherman
MAJOR REPAIR | 69 | MR-14 | 2025-30-07 | Original Governor's Mansion Heating & Fire Alarm | Helena | 300000 | A/E Appointed | 2026-05-28 | Q2 2026 | Design | Mark Hines
MAJOR REPAIR | 68 | MR-21 | 2023-04-03 | Repair / Replace Sewer Mains | Dillon | 815000 | A/E Appointed | 2026-05-30 | Q2 2026 | Design | Mark Hines
MAJOR REPAIR | 68 | MR-45 | 2023-05-03 | Campus EMS Building Controls Upgrade Project | Havre | 400000 | A/E Appointed | 2026-06-17 | Q2 2026 | Design | Chris Batson
MAJOR REPAIR | 69 | MR-36 | 2023-01-04A | Elevator System Upgrades | Missoula | 1675000 | A/E Appointed | 2026-06-30 | Q2 2026 | Planning | Mark Hines
AUTHORITY ONLY | 68 |  | 2023-11-01-02 | Install On-Campus Water Supply System | Warm Springs | 7500000 | A/E Appointed | 2026-06-30 | Q2 2026 | Design | Mark Hines
MAJOR REPAIR | 69 | MR-04 | 2025-01-02 | UM Selected Upgrades Exterior Steps Stairs Ramps | Missoula | 710000 | 2026-03-01 | 2026-07-01 | Q3 2026 | Planning | Nick Franz
CAPITAL DEVELOPMENT | 68 |  | 2023-35-08 | Agency Staff Housing Statewide | Statewide | 7500000 | A/E Appointed | 2026-07-01 | Q3 2026 | Design | Nick Franz
CAPITAL DEVELOPMENT | 68 |  | 2023-35-08-02 | Agency Staff Housing Statewide - Billings | Billings | 200000 | A/E Appointed | 2026-07-01 | Q3 2026 | Design | Nick Franz
CAPITAL DEVELOPMENT | 68 |  | 2023-35-08-01 | Agency Staff Housing Statewide - Cardwell | Cardwell | 300000 | A/E Appointed | 2026-07-01 | Q3 2026 | Design | Nick Franz
CAPITAL DEVELOPMENT | 68 |  | 2023-35-08-03 | Agency Staff Housing Statewide - Kalispell | Kalispell | 100000 | A/E Appointed | 2026-07-01 | Q3 2026 | Design | Nick Franz
CAPITAL DEVELOPMENT | 68 |  | 2023-33-20 | State Emergency Coordination Center Expansion | Helena | 6581000 | A/E Appointed | 2026-07-07 | Q3 2026 | Design | Chris Batson
CAPITAL DEVELOPMENT | 69 | CD-24 | 2025-33-04 | SMART Deferred Maintenance Program Statewide | Statewide | 6000000 | 2026-03-10 | 2026-07-14 | Q3 2026 | Planning | Nick Franz
CAPITAL DEVELOPMENT | 69 | CD-34 | 2023-35-10-01 | Central Services Site Upgrades Phase 2 | Helena | 13350000 | A/E Appointed | 2026-07-16 | Q3 2026 | Design | Nick Franz
CAPITAL DEVELOPMENT | 69 | CD-35 | 2023-35-10-02 | Central Services Site Upgrades Phase 3 | Helena | 16680000 | A/E Appointed | 2026-07-16 | Q3 2026 | Design | Nick Franz
MAJOR REPAIR | 69 | MR-22 | 2025-07-03 | UM HC Donaldson Campus Roofing Replacement | Helena | 2400000 | 2026-03-27 | 2026-07-20 | Q3 2026 | Planning | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-73 | 2025-01-07 | New Bandy Ranch Field Research Housing | Missoula | 2000000 | 2026-03-01 | 2026-08-11 | Q3 2026 | Planning | Nick Franz
MAJOR REPAIR | 69 | MR-50 | 2025-33-XX | FTH Building 1009 New Generator | Ft. Harrison | 255000 | 2026-01-30 | 2026-09-25 | Q3 2026 | Planning | Mark Hines
MAJOR REPAIR | 69 | MR-07 | 2025-12-03 | MSP MCE New Emergency Generators | Deer Lodge | 200000 | 2026-02-27 | 2026-09-25 | Q3 2026 | Planning | Mark Hines
CAPITAL DEVELOPMENT | 69 | CD-22 | 2025-02-11 | Hamilton Hall 3rd & 4th Floor Renovation | Bozeman | 5230000 | A/E Appointed | 2026-09-29 | Q3 2026 | Design | Marina Little
MAJOR REPAIR | 69 | MR-34 | 2025-12-05 | MSP Gravel Pit Equipment Generator Replacement | Deer Lodge | 180000 | 2026-02-27 | 2026-09-30 | Q3 2026 | Planning | Mark Hines
CAPITAL DEVELOPMENT | 68 | CD-25 | 2023-01-09 | Clapp Building Replacement (Forestry combined) | Missoula | 72000000 | A/E Appointed | 2026-10-01 | Q4 2026 | Design | Russ Katherman
MAJOR REPAIR | 69 | MR-33 | 2025-02-08 | MSU South Campus Primary Electrical Distribution U | Bozeman | 1750000 | 2026-01-30 | 2026-10-15 | Q4 2026 | Planning | Mark Hines
MAJOR REPAIR | 69 | MR-25 | 2025-06-01 | Campus-Wide Electrical Distribution Upgrades | Butte | 1300000 | A/E Appointed | 2026-10-15 | Q4 2026 | Planning | Mark Hines
MAJOR REPAIR | 69 | MR-39 | 2025-20-01 | Selected HVAC Systems Upgrades | Great Falls | 2000000 | 2026-01-21 | 2026-10-20 | Q4 2026 | Planning | Chris Batson
MAJOR REPAIR | 69 | MR-03 | 2025-07-01 | Missoula College West Mechanical, Electrical & Acc | Missoula | 2200000 | 2026-01-30 | 2026-10-25 | Q4 2026 | Planning | Mark Hines
MAJOR REPAIR | 68 | MR-28 | 2023-02-24 | Lewis Hall ADA Upgrades | Bozeman | 7000000 | A/E Appointed | 2026-11-15 | Q4 2026 | Design | Marina Little
MAJOR REPAIR | 69 | MR-31 | 2023-15-02-01 | PHYCF Utility Tunnel & Heating System Repairs | Miles City | 1200000 | A/E Appointed | 2026-11-17 | Q4 2026 | Planning | Chris Batson
MAJOR REPAIR | 69 | MR-18 | 2025-30-08 | State Print & Mail Building Roof Replacement | Helena | 825000 | 2026-03-09 | 2026-11-18 | Q4 2026 | Planning | Marina Little
MAJOR REPAIR | 69 | MR-29 | 2025-45-01 | Montana Learning Center Site Infrastructure Upgrad | Canyon Ferry Lake | 700000 | 2026-01-20 | 2026-12-15 | Q4 2026 | Planning | Mark Hines
MAJOR REPAIR | 69 | MR-08 | 2025-30-06 | ASF Shop Building New Fire Suppression System | Helena | 950000 | 2026-07-15 | 2026-12-15 | Q4 2026 | Planning | Chris Batson
CAPITAL DEVELOPMENT | 68 | CD-13 | 2016-01-01-03 | FLBS Water & Sewer Systems | Yellow Bay | 2500000 | A/E Appointed | 2027-01-15 | Q1 2027 | Planning | Mark Hines
CAPITAL DEVELOPMENT | 68 |  | 2023-05-07 | MSU-N Health & Rec Ctr, Aurora Complex | Havre | 25000000 | A/E Appointed | 2027-01-21 | Q1 2027 | Design | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-15 | 2025-30-14 | Capitol Complex Elevator System Upgrades | Helena | 5700000 | 2026-03-31 | 2027-01-28 | Q1 2027 | Planning | Mark Hines
CAPITAL DEVELOPMENT | 69 | CD-11 | 2025-30-13 | Capitol Complex Roof Replacements | Helena | 4100000 | 2026-04-30 | 2027-01-29 | Q1 2027 | Planning | Marina Little
MR/AO | 69 |  | 2025-02-10 | MSU Replace Failed Data Center Cooling Systems | Bozeman | 1300000 | 2026-03-31 | 2027-01-31 | Q1 2027 | Planning | Mark Hines
CAPITAL DEVELOPMENT | 68 |  | 2025-07-05 | Gallatin College | Bozeman | 46000000 | 2026-06-01 | 2027-02-01 | Q1 2027 | On Hold | Nick Franz
AUTHORITY ONLY | 69 |  | 2025-06-05 | Campus Expansion & Upgrades | Butte | 50000000 | TBD | 2027-02-01 | Q1 2027 | On Hold | Nick Franz
CAPITAL DEVELOPMENT | 69 | CD-13 | 2025-07-04 | Highlands College Roof Replacement | Butte | 5000000 | 2026-02-02 | 2027-02-03 | Q1 2027 | Planning | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-36/37 | 2025-35-01 | State Park Storage Building at Cooney Park & Dead |  | 375000 | 2026-07-06 | 2027-02-04 | Q1 2027 | Planning | Marina Little
MAJOR REPAIR | 69 | MR-40 | 2025-02-09 | MSU McCall Hall Demolition | Bozeman | 1400000 | 2026-08-06 | 2027-02-06 | Q1 2027 | Planning | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-25 | 2025-12-08 | Construction Education Program Bldg & Old Territor | MSP | 4200000 | A/E Appointed | 2027-02-15 | Q1 2027 | Planning | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-12 | 2025-01-04 | Selected Roof Replacements | Missoula | 3000000 | 2026-05-01 | 2027-03-01 | Q1 2027 | Planning | Nick Franz
CAPITAL DEVELOPMENT | 69 | CD-06 | 2025-01-03 | Classrooms & Teaching Labs Modernization | Missoula | 11600000 | 2026-06-01 | 2027-03-01 | Q1 2027 | Planning | Nick Franz
MAJOR REPAIR | 69 | MR-12 | 2025-37-01 | Boulder MHP/IBC Campus Heating System Upgrades | Boulder Campus | 2350000 | 2026-08-15 | 2027-03-16 | Q1 2027 | Planning | Chris Batson
CAPITAL DEVELOPMENT | 69 | CD-21 | 2025-01-06 | Mansfield Library Renovation | Missoula | 18000000 | 2026-10-01 | 2027-04-01 | Q2 2027 | Planning | Nick Franz
CAPITAL DEVELOPMENT | 69 | CD-18 | 2025-01-05 | Music Building Renovation | Missoula | 14500000 | 2026-10-01 | 2027-04-01 | Q2 2027 | Planning | Nick Franz
CAPITAL DEVELOPMENT | 69 | CD-14 | 2025-03-02 | Cisel Hall HVAC & Plumbing System Upgrades | Billings | 4000000 | 2026-06-10 | 2027-04-14 | Q2 2027 | Planning | Chris Batson
MAJOR REPAIR | 69 | MR-24 | 2025-30-09 | ASF Hangar Door Reconstruction & Replacement | Helena | 320000 | 2026-10-29 | 2027-04-20 | Q2 2027 | Planning | Chris Batson
MAJOR REPAIR | 69 | MR-20 | 2025-25-01 | EMVH Water Infiltration & Exterior Envelope Repair | Glendive | 1900000 | 2027-01-12 | 2027-04-21 | Q2 2027 | Planning | Chris Batson
CAPITAL DEVELOPMENT | 69 | CD-67/68/6 | 2025-31-01 | ESBs at Three Forks, Wolf Creek, Lodge Grass, Conr |  | 5300000 | 2026-05-01 | 2027-05-01 | Q2 2027 | Planning | Nick Franz
CAPITAL DEVELOPMENT | 69 | CD-07 | 2025-38-01 | New Forestry & Trust Lands Office Building | Missoula | 2000000 | 2026-08-01 | 2027-05-01 | Q2 2027 | Planning | Nick Franz
CAPITAL DEVELOPMENT | 69 | CD-16 | 2025-20-02 | Vocational Building Renovation Demolition & New C | Great Falls | 4000000 | 2026-10-14 | 2027-05-11 | Q2 2027 | Planning | Chris Batson
CAPITAL DEVELOPMENT | 69 | CD-28 | 2025-37-03 | New Indoor Firing Range | Helena | 10000000 | 2026-07-01 | 2027-06-01 | Q2 2027 | Planning | Russ Katherman
CAPITAL DEVELOPMENT | 69 | CD-23 | 2025-30-17 | 5 South Last Chance Gulch Building Renovation | Helena | 17300000 | 2026-06-14 | 2027-06-14 | Q2 2027 | Planning | Marina Little
MAJOR REPAIR | 69 | MR-42 | 2025-30-11 | Capitol Complex Restroom Renovations | Helena | 625000 | 2026-09-14 | 2027-08-26 | Q3 2027 | Planning | Marina Little
CAPITAL DEVELOPMENT | 68 | CD-23 | 2023-07-02 | Acquire & Renovate Airport Hangar | Helena | 3600000 | 2026-03-18 | 2027-09-30 | Q3 2027 | Planning | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-75 | 2025-02-12D | Instructional Space Modernization | Bozeman | 4000000 | 2026-04-06 | 2027-10-07 | Q4 2027 | DELEGATED | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-81 | 2024-02-05 | Visual Communications Building Classroom Addition | Bozeman | 11500000 | 2026-03-16 | 2027-10-27 | Q4 2027 | DELEGATED | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-76 | 2025-01-08 | Law School Interior Remodel | Missoula | 3000000 | 2027-02-01 | 2027-11-01 | Q4 2027 | Planning | Nick Franz
CAPITAL DEVELOPMENT | 69 | CD-72 | 2025-03-03 | New Art Building | Billings | 13400000 | 2026-07-06 | 2028-01-20 | Q1 2028 | Planning | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-19 | 2025-30-15 | 1227 11th Avenue Renovation | Helena | 3600000 | 2027-01-11 | 2028-01-27 | Q1 2028 | Planning | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-20 | 2025-30-16 | 1300 11th Avenue Renovation | Helena | 4150000 | 2027-01-11 | 2028-01-27 | Q1 2028 | Planning | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-79 | 2025-01-09 | Undergraduate Research Lab Upgrades & Improvements | Missoula | 10000000 | 2027-02-01 | 2028-02-01 | Q1 2028 | Planning | Nick Franz
MAJOR REPAIR | 68 | AO MR-03 | 2023-12-04 | MCE Industries Repairs | Deer Lodge | 700000 | A/E Appointed | 2028-03-29 | Q1 2028 | Planning | Marina Little
MAJOR REPAIR | 69 | MR-35 | 2025-42-01 | Kalispell Job Service Renovations | Kalispell | 325000 | 2026-07-13 | 2028-07-13 | Q3 2028 | Planning | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-29 | 2025-33-06 | MT State Veterans' Cemetery New Interment Processi | Helena | 600000 | 2026-10-26 | 2028-10-26 | Q4 2028 | Planning | Marina Little
CAPITAL DEVELOPMENT | 68 |  | 2023-33-18 | Billings Readiness & Innovation Campus (BRIC) | Billings | 78840000 | A/E Appointed | 2031-05-20 | Q2 2031 | On Hold | Chris Batson
MAJOR REPAIR | 68 | MR-30 | 2023-02-25 | Tietz Hall Roof Replacement | Bozeman | 1300000 | A/E Appointed |  |  | On Hold | Marina Little
AUTHORITY ONLY | 68 | AO-01 | 2023-01-13D | McGill Hall Expansion | Missoula | 6000000 | A/E Appointed |  |  | DELEGATED
CAPITAL DEVELOPMENT | 68 |  | 2024-30-02-01 | Cogswell Building Renovation | Helena | 50000 | A/E Appointed |  |  | On Hold | Russ Katherman
MAJOR REPAIR | 68 |  | 2023-30-07 | Cogswell Building Elevator Modifications | Helena | 768757 | A/E Appointed |  |  | On Hold | Marina Little
| 68 |  | 2023-35-09 | Miles City Train Depot Renovation | Miles City | 2000000 | A/E Appointed |  |  | On Hold | Marina Little
CAPITAL DEVELOPMENT | 69 | CD-74 | 2024-01-01D | Bio Research Building Addition | Missoula | 8000000 | A/E Appointed |  |  | DELEGATED
CAPITAL DEVELOPMENT | 68 |  | 2024-30-02 | Capitol Complex Building Renovations | Helena | 36557188.52 | A/E Appointed |  |  | Planning | Russ Katherman
CAPITAL DEVELOPMENT | 68 |  | 2024-30-03 | LAD Relocation | Helena | 16500000 | A/E Appointed |  |  | Planning | Russ Katherman
MAJOR REPAIR | 68 | MR-46 | 2018-30-07 | FCA Baseline Assessments | Statewide | 1500000 | A/E Appointed |  |  | Planning | Steve Faherty
CAPITAL DEVELOPMENT | 69 | CD-49 | 2025-35-02D | Lewis & Clark Caverns State Park Water System | Whitehall | 1385000 | A/E Appointed |  |  | DELEGATED
MAJOR REPAIR | 69 |  | 2025-33-03D | FTH MIST/MINER Facility Upgrade | Ft. Harrison | 1900000 | A/E Appointed |  |  | DELEGATED | N/A
CAPITAL DEVELOPMENT | 69 | CD-09 | 2025-38-02 | Bunkhouses: Helena, Plains & Libby (w/Office Addn) |  | 2100000 | A/E Appointed |  |  | On Hold | Nick Franz
MAJOR REPAIR | 69 |  | 2026-37-01 | MLEA Campus Infrastructure Feasiblity Study | Helena | 79490 | A/E Appointed |  |  | Planning | Mark Hines
MAJOR REPAIR | 68 |  | 2011-11-01-06 | MSH Wastewater Treatment Biofilter & Collection | Warm Springs | 601386 | A/E Appointed |  |  | Design | Mark Hines
AUTHORITY ONLY | 68 |  | 2024-38-01 | NW Land Office Lighting Upgrade | Kalispell | 20000 | Direct Select |  |  | On Hold | Mark Hines
| 68 |  | 2024-38-02 | Stillwater Unit Energy Upgrade | Olney | 10000 | Direct Select |  |  | On Hold | Mark Hines
CAPITAL DEVELOPMENT | 68 | AO CD-09 | 2023-07-03 | Highlands College Indoor Pole Barn | Butte | 2000000 |  |  |  | On Hold | Marina Little
| 68 |  | 2023-37-02 | Crime Lab Facility & Morgue Upgrade | Missoula | 2000000 |  |  |  | On Hold | Mark Hines
CAPITAL DEVELOPMENT | 69 | CD-31 | BEC | Capital Development Projects Planning Studies | Helena | 2000000 |  |  |  | Planning | Russ Katherman
CAPITAL DEVELOPMENT | 69 | CD-78 | 2025-02-13D | Nopper Building Purchase | Bozeman | 6500000 |  |  |  | DELEGATED | Russ Katherman
MAJOR REPAIR | 69 | MR-47 | 2025-30-12 | Statewide Selected Feasibility Studies for Agencie | N/A | 500000 |  |  |  |  | TBD
CONSULTANTS:
Projects < or = $2.5M: Direct Select
Projects > $2.5M: RFQ
CONTRACTORS:
Bid Dates /Quarters are preliminary and may change.